## Single Site Plan (hidden)
Task | One Time Task vs Repeat Task | Dependencies | Est. Duration (hours) | Owner | Planned Start | Planned Finish | Actual Start | Actual Finish | Timeline | Notes / Comments
Avathon Internal Pre Deployment Kick Off
Identify internal staffing(QA/DevOps Engineer/Tech Support)
Zoho/Time tracking set up
Set up internal slack channels, project folders in Services Sharepoints
Create project plan, invoice schedule
Update Zoho projections based on project plan
Share projections with Finance
Hold Internal Kick off with Program Team, Sales, Product
Discovery and Planning
Customer Kick Off Meeting
In Person Discovery Workshop for requrements gathering (use case deep dives, success criteria finalization, data collection - videos)
Plan and Document validation scenarios for the use cases
Update project timelines and share updated project plan with customer
Weekly Cadence Meeting setup between Customer site and Avathon
Hardware - Procurement
FInalize # of Cameras per site and Total Cameras - 10 Cameras per site
Finalize Identification and Procurement of Edge Devices - 1 Device Per Site
Procure EdgeDevice Hardware
Hardware - Setup and Configuration
Install necessary OS and other software dependencies on the EdgeDevice
Validate to make sure that EdgeDevice is set-up as per the product requirement (This can be done offline at Avathon Facility or Customer Facility)
Install all the cameras configured at Austin, TX office for Internal Testing
Software - Setup and Configuration (at Avathon Office)
Install VAIA software on EdgeDevice Server
Configure VAIA Edge application with VAIA Core Dashboard Application
Validate VAIA Edge and Core connectivity from the Application Deployment Dashboard
Deploy Identified Modules and Use Cases, Configure Use Case Parameters
Fine Tune, Configure and Validate Camera angles, height, ROI to confirm optimized working of each use case deployed
Deploy any software patch or upgrade to make sure that all Use Cases are working as per the requirements.
Data collection for set-up
Set up test environment
Verification
Software - Setup and Configuration (at Customer Site)
VPN Connectivity from Customer Site to Avathon
All Cameras details and connectivity to the EdgeDevice
Deploy and Configure all Use Cases to each of the Cameras connected to Edge Device
User Accounts Creation to access Dashboard and receive Alerts/Notifications
Use Cases Validation, Iteration, Model Updates
Iterate on model performance and improve accuracy
Adjust configurations as needed, ROI
Validation/Testing - end to end of all use cases, scenarios
(Internal Testing) Validate that all use cases are working in PROD @ Avathon Site
Enable access for customer to the dashboard
User Training Document Preparation and Training Users (User Management, Dashboard Alarm Review, Alerts/Notification Configuration)
Customer Feedback and Updates (Iterate)
Gather customer feedback
Adjust configuration, settings, models as needed.
Monitoring and Support
Proactive Monitoring to make sure everything works fine - violations, alerts, notifications are getting generated correctily and all everything is showing up correctly in dashboard.

## Rollout-Tasks-Dependencies (hidden)
Task / Dependency | Original Planned Start | Original Planned Finish | Planned Start | Planned Finish | Actual Start | Actual Finish | Effort (Hours) | Status | Responsible Entity | Responsible Person | Notes / Comments
Discovery and Planning
Identify Key POC resources for project (QA/DevOps Engineer/Tech Support) | 2025-04-21 | 2025-04-29 | 2025-04-21 | 2025-04-29 |  |  |  | Completed | Avathon | Krishnan | Internally Resources are available on need basis (Sourabh, Sonali, Varun)
Finalization of Sites to be rolled out - 3 Sites Identified | 2025-04-21 | 2025-04-29 | 2025-04-21 | 2025-04-29 |  |  |  | Completed | Halliburton / Avathon | Jason/Krishnan | 2 sites information pending
Weekly Cadence Meeting setup between HAL and Avathon | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 |  |  |  | Completed | Avathon | Krishnan | Setting up weekly meeting to go over the overall project progress across all HAL Sites.
Hardware - Procurement
FInalize # of Cameras per site and Total Cameras - 10 Cameras per site | 2025-04-21 | 2025-04-30 | 2025-04-21 | 2025-04-30 |  |  |  | Completed
Finalize Identification and Procurement of Edge Devices - 1 Device Per Site | 2025-04-17 | 2025-05-06 | 2025-04-17 | 2025-05-06 |  |  |  | Completed | Halliburton / Avathon | Krishnan | Ordered 1 edge device for 1st site.
Procure EdgeDevice Hardware | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-04-30 |  |  |  | Completed | Halliburton / Avathon |  | Site-001 - Avathon procuring the device to speedup the implementation process 04/30/2025 - Devices Shipped to Avathon Austin Office
Hardware - Setup and Configuration
Install necessary OS and other software dependencies on the EdgeDevice | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed | Avathon | Krishnan / DevOps
Validate to make sure that EdgeDevice is set-up as per the product requirement (This can be done offline at Avathon Facility or Customer Facility) | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed | Avathon | Krishnan / DevOps
Install all the cameras configured at Austin, TX office for Internal Testing | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed | Halliburton / Avathon |  | At Avathon Austin Office Site a Camera is set-up and configured with the Edge Device with Use Cases Configured and basic testing done with the camera.
Software - Setup and Configuration (at Avathon Office)
Install VAIA software on EdgeDevice Server | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed |  | Krishnan / DevOps
Configure VAIA Edge application with VAIA Core Dashboard Application | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed |  | Krishnan / DevOps
Validate VAIA Edge and Core connectivity from the Application Deployment Dashboard | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed |  | Krishnan / DevOps
Deploy Identified Modules and Use Cases, Configure Use Case Parameters | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed |  | Krishnan /
Fine Tune, Configure and Validate Camera angles, height, ROI to confirm optimized working of each use case deployed | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed |  | Krishnan | With a single Camera installed and configured at Avathon Austin Office - this is validated.
Deploy any software patch or upgrade to make sure that all Use Cases are working as per the requirements. | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09 |  |  |  | Completed |  | Krishnan | As of 05/12/2025 - The EdgeDevice has the lasted VAIA Software installed.
Halliburton Shipped 3 Edge Devices, Camera, DVR to Austin, TX office to be configured with VAIA Edge Application, Validated and Shipped Back to their 3 sites. | 2025-06-23 | 2025-06-27 | 2025-06-23 | 2025-06-27 |  |  |  | Completed | Halliburton / Avathon | Krishnan / DevOps | Received all the devices, camera and DVR for set-up and configuration at Avathon TX office.
Ship all 3 Edge Devices to Duncan TCC, Ohio NE Site (#3), Rocky Mountain Site (#2) | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-11 |  |  |  | Completed |  | Krishnan / DevOps | Halliburton Provided 3 Edge Devices, 1 Camera and 1 DVR to Austin, TX office for them to be configured and tested with their Lorex Camera along with VAIA Edge Software Application.
Software - Setup and Configuration (at Halliburton Site) - Site #1
VPN Connectivity from Halliburton Site to Avathon | 2025-05-15 | 2025-07-18 | 2025-05-15 | 2025-07-18 |  |  |  | Completed | Halliburton | Halliburton / Avathon Teams | As of 05/12/2025 - The EdgeDevice is in the process of getting shipped to the 1st Site post that once the device is on the network the VPN connectivity needs to be established and configured. As of 07/08/2025 - Real VNC connectivity is established but not verified as the Edge Device is down.
All Cameras details and connectivity to the EdgeDevice | 2025-07-14 | 2025-07-18 | 2025-07-14 | 2025-07-18 |  |  |  | Completed | Halliburton | Halliburton / Avathon Teams | Camera Details are known - but IP address, user credentials still pending
Deploy and Configure all Use Cases to each of the Cameras connected to Edge Device | 2025-07-14 | 2025-07-18 | 2025-07-14 | 2025-07-18 |  |  |  | Completed | Avathon | Krishnan / DevOps | Only after Cameras are connected to the Edge Device - Use Cases can be added and configured.
User Accounts Creation to access Dashboard and receive Alerts/Notifications | 2025-07-14 | 2025-07-18 | 2025-07-14 | 2025-07-18 |  |  |  | Completed | Halliburton / Avathon | Krishnan / DevOps | Halliburton to provide list of users to be configured in the VAIA Application for them to view Dashboard , and receive Alerts / Notifications.
Sign-off from customer | 2025-08-16 | 2025-08-18 | 2025-08-16 | 2025-08-18 |  |  |  | Yet To Start
Software - Setup and Configuration (at Halliburton Site) - Site #2
Define use case requirements, scope for the pump optimization use case |  |  | TBD | TBD
VPN Connectivity from Halliburton Site to Avathon | 2025-07-21 | 2025-07-25 | TBD | TBD |  |  | NA | Yet To Start | Halliburton | Halliburton / Avathon Teams | 07/24 - Site #2 location may get changed from Rocky Mountain , CO to Permian Basin - Exact site details not known
All Cameras details and connectivity to the EdgeDevice | 2025-07-21 | 2025-07-25 | TBD | TBD |  |  | 8 | Yet To Start | Halliburton | Halliburton / Avathon Teams
Deploy and Configure all Use Cases to each of the Cameras connected to Edge Device | 2025-07-21 | 2025-07-25 | TBD | TBD |  |  | 8 | Yet To Start | Avathon | Krishnan / DevOps
User Accounts Creation to access Dashboard and receive Alerts/Notifications | 2025-07-21 | 2025-07-25 | TBD | TBD |  |  | 8 | Yet To Start | Halliburton / Avathon | Krishnan / DevOps
Software - Setup and Configuration (at Halliburton Site) - Site #3
VPN Connectivity from Halliburton Site to Avathon | 2025-07-21 | 2025-07-25 | 2025-08-11 | 2025-08-15 |  |  | NA | Yet To Start | Halliburton | Halliburton / Avathon Teams | 07/24 - No update from client on the date as to when this site the device will be set-up and operational.
All Cameras details and connectivity to the EdgeDevice | 2025-07-21 | 2025-07-25 | 2025-08-11 | 2025-08-15 |  |  | 8 | Yet To Start | Halliburton | Halliburton / Avathon Teams
Deploy and Configure all Use Cases to each of the Cameras connected to Edge Device | 2025-07-21 | 2025-07-25 | 2025-08-11 | 2025-08-15 |  |  | 8 | Yet To Start | Avathon | Krishnan / DevOps
User Accounts Creation to access Dashboard and receive Alerts/Notifications | 2025-07-21 | 2025-07-25 | 2025-08-11 | 2025-08-15 |  |  | 8 | Yet To Start | Halliburton / Avathon | Krishnan / DevOps
Red Zone Active/Inactive State API Integration (All Sites - Generic Solution)
Availability of API Details from Halliburton | 2025-07-21 | 2025-07-25 | 2025-07-15 | 2025-08-06 |  |  |  | In Progress | Halliburton |  | Discussion yet to happen with Halliburton about the availability of the API and how to Integrate.
API Integration Implementation | 2025-07-28 | 2025-08-08 | 2025-08-04 | 2025-08-08 |  |  | 80 | Yet To Start | Avathon |  | Pending API details from Halliburton
Validate successful working of Red Zone State Recognition via Integration through API | 2025-08-11 | 2025-08-29 | 2025-08-08 | 2025-08-15 |  |  | 40 | Yet To Start | Halliburton / Avathon |  | Avathon and Halliburton Team will work together to get this validated.
Validation & Sign Off
(Internal Testing) Validate that all use cases are working in PROD @ Avathon Site | 2025-05-06 | 2025-05-11 | 2025-05-06 | 2025-05-11 |  |  | 16 | Completed | Avathon | Krishnan/QA | Configuration and Minimal Internal Testing completed for 1st site using Camera Installed at Avathon Austin Office.
Validate all Use Case Success Criteria - Site #1 | 2025-09-01 | 2025-09-19 | TBD | TBD |  |  | 40 | Yet To Start | Halliburton | Halliburton Team
Validate all Use Case Success Criteria - Site #2 | 2025-09-01 | 2025-09-19 | TBD | TBD |  |  | 40 | Yet To Start | Halliburton | Halliburton Team
Validate all Use Case Success Criteria - Site #3 | 2025-09-01 | 2025-09-19 | TBD | TBD |  |  | 40 | Yet To Start | Halliburton | Halliburton Team
User Training Document Preparation and Training Users (User Management, Dashboard Alarm Review, Alerts/Notification Configuration) | 2025-09-01 | 2025-09-05 | TBD | TBD |  |  | 24 | Yet To Start | Halliburton / Avathon | Avathon Team | Online Guides are available - users need to be trained with User Management, Alarm Dashboard, Verify/Ack/Close Alarms, Notification set-up etc...
Standardize Enterprise Rollout - All Sites
Align on any custom use cases for all sites | 2025-09-08 | 2025-09-12 | TBD | TBD |  |  |  | Yet To Start | Halliburton
Develop production deployment plan and review with the site team for all future sites | 2025-09-15 | 2025-09-19 | TBD | TBD |  |  | 16 | Yet To Start | Halliburton / Avathon | Krishnan / DevOps
Monitoring and Support for 3 POC Sites
1 week of hypercare to make sure everything works fine - violations, alerts, notifications are getting generated correctily and all everything is showing up correctly in dashboard. | 2025-09-01 | 2025-09-30 | 2025-09-01 | 2025-09-30 |  |  | NA | Yet To Start | Halliburton / Avathon
Old Format - Do not Use

## Project Plan - First Site (hidden)
Task
This plan is based on customer with no existing CCTV infra
Check- Point |  | Status | Post Contract sign off | Owner | Effort (hours) | Ref Document | Comment | Planned Start | Planned Finish | Actual Start | Actual Finish
New Milestone
Project Readiness | Pre Deployment |  | Avathon Internal Pre Deployment Kickoff
|  | TRUE | Identify internal staffing(QA/DevOps Engineer/Tech Support) | Program Manager | 1 |  |  | 2025-04-21 | 2025-04-29 | 2025-04-21 | 2025-04-29
|  | TRUE | Zoho/Time tracking set up | Program Manager | 4 |  | Back in April Smartsheet was being used and we replaced it with Zoho Time Sheet tool and rolled out for PSG in 1st week of May | 2025-04-28 | 2025-04-28 | 2025-05-05 | 2025-05-05
|  | TRUE | Set up internal slack channels, project folders in Services Sharepoints | Program Manager | 1 |  |  | 2025-04-21 | 2025-04-29 | 2025-04-21 | 2025-04-29
|  | TRUE | Create project plan | Program Manager | Continuous activity |  | Continue to update and review project plan | 2025-04-21 | 2025-04-29 | 2025-05-05
|  | FALSE | Create invoice schedule | Program Manager |  |  | TBC with finance. 8 days T&M invoice for site 1 sent to Halliburton; 7 days pending. | 2025-09-01 | 2025-09-01
|  | FALSE | Update Zoho projections based on project plan | Program Manager | 8 |  | Zoho doesn't have option to capture projections currently
|  | TRUE | Share projections with Finance | Program Manager | 4 |  |  | 2025-04-21 | 2025-04-29 | 2025-04-21 | 2025-04-29
|  | TRUE | Hold Internal Kick off with Program Team, Sales, Product | Program Manager | 8 |  |  | 2025-04-21 | 2025-04-29 | 2025-04-21 | 2025-04-29
|  | FALSE | Completion Criteria for SOW Activity 1: Project Governance Plan | Program Manager |  | 1. This document 2. Email to customer POC to align on general project governance |  | 2025-08-12 | 2025-08-15
| Planning |  | Discovery & Planning |  |  | HPCL FDS - Reference Doc
|  | FALSE | Customer Kick Off Meeting | Program Manager | 2 |  | Plan to have kickoff meeting when site 2 requirements are scoped out | 2025-08-15 | 2025-08-15
|  | TRUE | Discovery Workshop for requirements gathering (deployment environment, solution functional requirements, and solution success criteria) | Program Manager | 8 |  | Documents are pending from product for site 2 requirements | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05
|  | FALSE | Validate architecture requirements with IT and system integration stakeholders | Program Manager | 8 | Avathon-VAIA-Architecture-Hardware.pptx | As part of Pre-Sales meeting with the customer - the referenced VAIA Architecture diagram was shared with the customer. Any further update to new requirements will be captured | 2025-08-18 | 2025-08-25
|  | FALSE | Validate functional requirements, business pain points, success metrics with operational and end user stakeholders | Program Manager |  | Functional Design Specification | Same as above | 2025-08-18 | 2025-08-25
|  | FALSE | Document use cases, scenarios, expected behaviour | Program Manager | 4 | Site 1 Use Cases (don't share with customer - re-check) | Sign off pending from customer | 2025-08-12 | 2025-08-12
|  | TRUE | Request security clearance to access camera feed, and general access to customer sites, assets, etc. | Program Manager |  |  |  | 2025-08-05 | 2025-08-08
|  | FALSE | Existing hardware and Exisiting camera footage (If Applicable) | Program Manager | 4 |  | N/A here since customer had no existing infra
|  | FALSE | Plan and Document validation scenarios for the use cases | Program Manager |  |  | Pending for site 2 | 2025-08-18 | 2025-08-18
|  | TRUE | Update project timelines and share updated project plan with customer | Program Manager |  | Customer meeting on 8/5 |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29
|  | TRUE | Weekly Cadence Meeting setup between Customer site and Avathon | Program Manager | 0 | On Going Continuous Activity |  | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29
|  | FALSE | Completion Criteria for SOW Activity 2: Functional Design Spec, Kickoff Meeting Deck | Program Manager |  | Functional Design Specification |  | 2025-08-19 | 2025-08-19
| Procurement |  | Hardware - Procurement |  |  | Purchase Order
|  | TRUE | FInalize # of Cameras per site and Total Cameras - up to 10 Cameras per site | Customer |  |  | Identified 2 Cameras Per Site to be used | 2025-04-21 | 2025-04-30 | 2025-04-21 | 2025-04-30
|  | TRUE | Finalize Identification and Procurement of Edge Devices - 1 Device Per Site (if applicable) | Customer |  | EdgeServerOrderReceipt.pdf | Placed Edge Device Order On April 17 and Received the Device on April 30th | 2025-04-17 | 2025-05-02 | 2025-04-17 | 2025-05-02
Check- Point |  |  | Planning and Hardware Procurement Complete
Milestone |  |  | Hardware - Setup and Configuration (production site - RK_FTL_WARTHOGS) ** starts after the hardware is received by Avathon
Hardware Setup & Configuration | Edge device setup (at Avathon/customer site) | TRUE | Access to the edge device and install Ubuntu 24 | FE-DevOps | 4 |  |  | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09
|  | TRUE | Install other software dependencies on the EdgeDevice | FE-DevOps | 8 |  |  | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09
|  | TRUE | Validate to make sure that EdgeDevice is set up as per the product requirement (This can be done offline at Avathon Facility or Customer Facility get sample videos and data points) | FE-DevOps | 4 |  |  | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-09
|  | TRUE | Run and Validate product usecases on the sample vidoo feed / test camera (FE Testing) | FE-testing | 24 |  | After Setting up the Edge Device at Avathon Austin Location - Internal testing of Use Cases were performed with live Camera Installed at Austin Office. | 2025-05-06 | 2025-05-09 | 2025-05-07 | 2025-05-09
|  | TRUE | Ship the edge device to Customer Site (shipping and transportation) | Customer/Program Manager | 1 |  |  | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12
| Camera Access (at customer site) | TRUE | VPN Connectivity from Customer Site to Avathon | Customer |  |  | After the Device was shipped to customer site on May 12th took much longer time from the customer Network/Security/IT team to get the device on to the network and provide access. | 2025-05-15 | 2025-07-18 | 2025-05-15 | 2025-07-18
|  | TRUE | Edge device is connected to the camera network with internet | Customer | 8 |  | Once the Edge Device was accessible in the week of July 14 camera connectivity, configuration and testing was performed. | 2025-07-14 | 2025-07-18 | 2025-07-14 | 2025-07-18
|  | TRUE | Access to the camera- Access to IP Address and Configuration | Customer | 8 |  | Week of July 21 Camera was fully connected and configured with the use cases. | 2025-07-14 | 2025-07-18 | 2025-07-21 | 2025-07-22
|  | TRUE | Access to the camera- User credentials | Customer | 2 |  | Week of July 21 Camera was fully connected and configured with the use cases. | 2025-07-14 | 2025-07-18 | 2025-07-21 | 2025-07-28
Check- Point |  |  | Hardware Ready & Configuration Complete
Milestone |  |  | Testing
Testing & model training | Feed access | TRUE | Camera feed access to the Forward Engineering team | Customer
| Whitelisting | TRUE | Whitelisting our URL and IP | Customer |  |  | Device was shipped to customer site on May 12th but it was available to verify on week of July | 2025-05-12 | 2025-05-16 | 2025-07-07 | 2025-07-11
| Model Training with offline videos | FALSE | Data collection for training | FE-CV | 40 |  |  | 2025-08-18 | 2025-08-25
|  | FALSE | Model training | FE- CV | 40 |  |  | 2025-08-18 | 2025-08-25
|  | FALSE | Testing on additional videos | FE-Testing | 48 |  |  | 2025-08-25 | 2025-08-29
| Usecase camera configuration (remotely) | TRUE | Drawing ROI | FE-DevOps | 8 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21
|  | TRUE | Deployment of the usecases, configuring use case parameters | FE-DevOps | 4 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21
|  | FALSE | Internal sign off for use case scenario testing | FE-DevOps
| Model Tuning and Re-training | FALSE | Standard use case and scenario testing
|  | FALSE | Customer specific use case and scenario testing
|  | FALSE | Ongoing model retraining
|  | FALSE | Ongoing synthetic condition testing
|  | FALSE | Send test evidence to customer
| Dashboard setup | TRUE | Configure VAIA Edge application with VAIA Core Dashboard Application (sites, camera setup) | FE-Testing | 4 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21
|  | TRUE | Validate VAIA Edge and Core connectivity (API validation) from the Application Deployment Dashboard | FE-DevOps | 8 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21
|  | TRUE | Fine Tune, Configure and Validate Camera angles, height, ROI to confirm optimized working of each use case deployed | FE-testing | 16 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21
|  | TRUE | Proactive Monitoring | Program Manager | Continouus activity |  |  | 2025-07-21 |  | 2025-07-21
|  | TRUE | Deploy any software patch or upgrade to make sure that all Use Cases are working as per the requirements. | FE-DevOps | 16 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21
| Internal and Customer Signoffs | FALSE | Verification and internal signoff- F1 scores to be above 0.9 | Program Manager/ Testing | 16 |  | Dependency on Site 2 pump use case | 2025-08-25 | 2025-08-29
|  | FALSE | Completion Criteria for SOW Activities 3 & 4: Customer specific use case and scenario test results and accuracy reports | Program Manager/ Testing |  | Accuracy Report - TBD |  | 2025-08-29 | 2025-09-01
Check- Point we are now here🏁 |  |  | Customer Live Ready
Milestone |  |  | Customer User setup - Training & Hand over |  |  | User Training Guide - TBD
Handover to Client | Demo | TRUE | Stakeholder demo | Forward Engineering ** (hours for 1 FTE) | 4
| Solution fine-tuning | FALSE | Adjust configurations as needed, ROI | FE-DevOps | 8
| Proactive Monitoring | TRUE | Proactive Monitoring | Program Manager | Continouus activity |  |  | 2025-07-21 |  | 2025-07-21
| User set up and training | TRUE | User Accounts Creation to access Dashboard and receive Alerts/Notifications | Program Manager | 4 |  |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24
|  | FALSE | User Training Document Preparation and Training Users on recorded sessions (User Management, Dashboard Alarm Review, Alerts/Notification Configuration). And training the clients as to how to raise tickets | FE- Testing/ Support | 4
|  | FALSE | Customer UAT and simulations in prod environment | Customer
|  | FALSE | Completion Criteria for SOW Activity 5 |  |  | User training guide, recorded training sessions
331
Milestone |  |  | Customer Feedback and Updates (Iterate) |  |  | HPCL SAT Report - Reference Doc
Sign off |  | FALSE | Gather customer feedback | Program Manager |  |  |  | 2025-09-08 | 2025-09-12
|  | FALSE | Get sign off , Approval for the 1 site | Program Manager/Executive |  | SAT (Site Acceptance Test) Report - TBD
Check- Point |  |  | Move to Support
|  | FALSE | Get roll out info for rest of the sites | Program Manager |  |  |  | 2025-09-12 | 2025-09-12
Milestone |  |  | Monitoring and Support
Monitoring and Support | Monitoring | FALSE | Proactive Monitoring to make sure everything works fine - violations, alerts, notifications are getting generated correctily and all everything is showing up correctly in dashboard. | Support
|  | FALSE | Performance monitoring | Support
| Ticketing | FALSE | Track the false alerts, issue Resolution | Support
Old Format - Do not Use
Note on M1: Dhamini R Nijgal: =F$1<=$B2 =AND(F$1>$B2,F$1<=$B2+$C2) =AND(F$1>$B2+$C2,F$1<=$B2+$C2+$D2) =AND(F$1>$B2+$C2+$D2)

## Project Plan - Sites 1
[6 empty] | Project Start: | 2025-04-17
| Sites: 1 |  |  |  |  | Today: | 2025-08-13
[6 empty] | Display Week: | 8 |  |  | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08
 | time axis 2025-06-02 to 2025-12-14
| TASK | OWNER | COMMENT | REF LINK | EST. EFFORT (HRS) | PROGRESS | START | END | DAYS | time axis 2025-06-02 to 2025-12-14
| Avathon Internal Project Setup |  |  |  | 34 | 100% | 2025-04-21 | 2025-08-05 | 107
Internal Planning & Setup | Identify internal staffing(QA/DevOps Engineer/Tech Support) | Program Manager |  |  | 1 | 100% | 2025-04-21 | 2025-04-29 | 9
| Zoho/Time tracking set up | Program Manager | Back in April Smartsheet was being used and we replaced it with Zoho Time Sheet tool and rolled out for PSG in 1st week of May |  | 4 | 100% | 2025-05-05 | 2025-05-05 | 1
| Set up internal slack channels, project folders in Services Sharepoints | Program Manager |  |  | 1 | 100% | 2025-04-21 | 2025-04-29 | 9
| Create project plan | Program Manager | Continue to update and review project plan |  | 4 | 100% | 2025-07-28 | 2025-08-04
| Create invoice schedule | Program Manager | TBC with finance. 8 days T&M invoice for site 1 sent to Halliburton; 7 days pending. |  | 4 | 100% | 2025-07-29 | 2025-07-29
| Update Zoho projections based on project plan | Program Manager | Zoho doesn't have option to capture projections currently |  | 8 | 100%
| Share projections with Finance | Program Manager |  |  | 4 | 100% | 2025-04-21 | 2025-04-29
| Hold Internal Kick off with Program Team, Sales, Product | Program Manager |  |  | 8 | 100% | 2025-04-21 | 2025-04-29
| Completion Criteria for SOW Activity 1: Project Governance Plan | Program Manager | 1. This document or in Halliburton's case, the project plan shared in the weekly meetings 2. Email to customer POC to align on general project governance | Weekly Meeting Decks |  | 100% | 2025-07-29 | 2025-08-05 | 8
| Discovery & Planning |  |  |  | 50 | 80.77% | 2025-04-17 | 2025-08-25 | 131
Planning | Customer Kick Off Meeting | Program Manager | Plan to have kickoff meeting when site 2 requirements are scoped out |  | 2 | 50% | 2025-08-15 | 2025-08-15 | 1
| Discovery Workshop for requirements gathering (deployment environment, solution functional requirements, and solution success criteria) | Program Manager | Documents are pending from product for site 2 requirements |  | 8 | 100% | 2025-05-05 | 2025-05-05 | 1
| Validate architecture requirements with IT and system integration stakeholders | Program Manager | As part of Pre-Sales meeting with the customer - the referenced VAIA Architecture diagram was shared with the customer. Any further update to new requirements will be captured | Avathon-VAIA-Architecture-Hardware.pptx | 8 | 100% | 2025-08-18 | 2025-08-25 | 8
| Validate functional requirements, business pain points, success metrics with operational and end user stakeholders | Program Manager | Same as above | Functional Design Spec | 8 | 50% | 2025-08-18 | 2025-08-25
| Document use cases, scenarios, expected behaviour | Program Manager | Sign off pending from customer |  | 4 | 50% | 2025-08-12 | 2025-08-12
| Request security clearance to access camera feed, and general access to customer sites, assets, etc. | Program Manager |  |  |  | 100% | 2025-08-05 | 2025-08-08
| Existing hardware and Exisiting camera footage (If Applicable) | Program Manager | N/A here since customer had no existing infra |  | 4 | 100% | 2025-04-21 | 2025-04-21
| Plan and Document validation scenarios for the use cases | Program Manager | Pending for site 2 |  | 8 | 50% | 2025-08-18 | 2025-08-18
| Update project timelines and share updated project plan with customer | Program Manager |  | Customer Meeting on 8/5 | 8 | 100% | 2025-07-29 | 2025-07-29
| Weekly Cadence Meeting setup between Customer site and Avathon | Program Manager |  |  |  | 100% | 2025-04-29 | 2025-04-29
| Completion Criteria for SOW Activity 2: Functional Design Spec, Kickoff Meeting Deck | Program Manager |  | Functional Design Spec |  | 50% | 2025-08-19 | 2025-08-19
Procurement | FInalize # of Cameras per site and Total Cameras - up to 10 Cameras per site | Customer | Identified 2 Cameras Per Site to be used |  |  | 100% | 2025-04-21 | 2025-04-30
| Finalize Identification and Procurement of Edge Devices - 1 Device Per Site (if applicable) | Customer | Placed Edge Device Order On April 17 and Received the Device on April 30th | EdgeServerOrderReceipt.pdf |  | 100% | 2025-04-17 | 2025-05-02
| Hardware Setup & Configuration |  |  |  | 59 | 100% | 2025-05-06 | 2025-07-28 | 84
Edge Device Setup (at Avathon / Customer Site) | Access to the edge device and install Ubuntu 24 | FE-DevOps |  |  | 4 | 100% | 2025-05-06 | 2025-05-09 | 4
| Install other software dependencies on the EdgeDevice | FE-DevOps |  |  | 8 | 100% | 2025-05-06 | 2025-05-09 | 4
| Validate to make sure that EdgeDevice is set up as per the product requirement (This can be done offline at Avathon Facility or Customer Facility get sample videos and data points) | FE-DevOps |  |  | 4 | 100% | 2025-05-06 | 2025-05-09 | 4
| Run and Validate product usecases on the sample vidoo feed / test camera (FE Testing) | FE-testing | After Setting up the Edge Device at Avathon Austin Location - Internal testing of Use Cases were performed with live Camera Installed at Austin Office. |  | 24 | 100% | 2025-05-07 | 2025-05-09
| Ship the edge device to Customer Site (shipping and transportation) | Customer/Program Manager |  |  | 1 | 100% | 2025-05-12 | 2025-05-12
Camera Access (at Customer Site) | VPN Connectivity from Customer Site to Avathon | Customer | After the Device was shipped to customer site on May 12th took much longer time from the customer Network/Security/IT team to get the device on to the network and provide access. |  |  | 100% | 2025-05-15 | 2025-07-18
| Edge device is connected to the camera network with internet | Customer | Once the Edge Device was accessible in the week of July 14 camera connectivity, configuration and testing was performed. |  | 8 | 100% | 2025-07-14 | 2025-07-18
| Access to the camera- Access to IP Address and Configuration | Customer | Week of July 21 Camera was fully connected and configured with the use cases. |  | 8 | 100% | 2025-07-21 | 2025-07-22
| Access to the camera- User credentials | Customer | Week of July 21 Camera was fully connected and configured with the use cases. |  | 2 | 100% | 2025-07-21 | 2025-07-28
| Testing & Model Traning |  |  |  | 208 | 61.11% | 2025-07-07 | 2025-09-01 | 57
| Camera feed access to the Forward Engineering team | Customer |  |  |  | 100%
| Whitelisting our URL and IP | Customer | Device was shipped to customer site on May 12th but it was available to verify on week of July |  |  | 100% | 2025-07-07 | 2025-07-11 | 5
Model Training with Offline Videos | Data collection for training | FE-CV |  |  | 40 | 30% | 2025-08-18 | 2025-08-25 | 8
| Model training | FE- CV |  |  | 40 | 30% | 2025-08-18 | 2025-08-25
| Testing on additional videos | FE-Testing |  |  | 48 | 30% | 2025-08-25 | 2025-08-29
Usecase Camera Configuration (remotely) | Drawing ROI | FE-DevOps |  |  | 8 | 100% | 2025-07-21 | 2025-07-21
| Deployment of the usecases, configuring use case parameters | FE-DevOps |  |  | 4 | 100% | 2025-07-21 | 2025-07-21
Model Tuning and Re-training | Standard use case and scenario testing | FE-Testing | Based on live alerts |  | 8 | 100% | 2025-07-30 | 2025-07-31
| Customer specific use case and scenario testing | FE-Testing | Customer dependent at the moment, cameras are offline. Awaiting progress and communication from Halliburton |  |  | 10%
| Ongoing model retraining | FE- CV | Dependent on tasks 50 and 51 |  |  | 0%
| Ongoing synthetic condition testing | Product and FE-Testing |  |  |  | 0%
Dashboard Setup | Configure VAIA Edge application with VAIA Core Dashboard Application (sites, camera setup) | FE-Testing |  |  | 4 | 100% | 2025-07-21 | 2025-07-21
| Validate VAIA Edge and Core connectivity (API validation) from the Application Deployment Dashboard | FE-DevOps |  |  | 8 | 100% | 2025-07-21 | 2025-07-21
| Fine Tune, Configure and Validate Camera angles, height, ROI to confirm optimized working of each use case deployed | FE-testing |  |  | 16 | 100% | 2025-07-21 | 2025-07-21
| Proactive Monitoring | Customer Support |  |  | Continuous activity | 50% | 2025-07-21
| Deploy any software patch or upgrade to make sure that all Use Cases are working as per the requirements. | FE-DevOps |  |  | 16 | 100% | 2025-07-21 | 2025-07-21
Internal and Customer Signoffs | Verification and internal signoff- F1 scores to be above 0.9 | Program Manager/ Testing | Continuous activity | F1 Scores - Report | 16 | 50% | 2025-08-25 | 2025-08-29
| Completion Criteria for SOW Activities 3 & 4: Customer specific use case and scenario test results and accuracy reports | Program Manager/ Testing |  | Accuracy Report |  | 0% | 2025-08-29 | 2025-09-01
| Customer User Setup: Training & Handover |  |  |  | 20 | 52.86% | 2025-07-21 | 2025-07-24
| Stakeholder demo | Forward Engineering |  |  | 4 | 100%
| Adjust configurations as needed, ROI | FE-DevOps |  |  | 8 | 100%
| Proactive Monitoring | Program Manager |  |  | Continuous activity | 50% | 2025-07-21
User setup and training | User Accounts Creation to access Dashboard and receive Alerts/Notifications | Program Manager |  |  | 4 | 100% | 2025-07-24 | 2025-07-24
| User Training Document Preparation and Training Users on recorded sessions (User Management, Dashboard Alarm Review, Alerts/Notification Configuration). And training the clients as to how to raise tickets | FE- Testing/ Support | User has received training on dashboard and creating additional users |  | 4 | 20%
| Customer UAT and simulations in prod environment | Customer |  |  |  | 0%
| Completion Criteria for SOW Activity 5 |  |  | User training guide, recorded training sessions |  | 0%
| Customer Feedback and Updates |  |  |  | 0 | 0% | 2025-09-08 | 2025-09-12
| Gather customer feedback | Program Manager |  |  |  | 0% | 2025-09-08 | 2025-09-12
| Get sign off , Approval for the 1 site | Program Manager/Executive |  | SAT (Site Acceptance Test) Report |  | 0%
| Move to Support |  |  |  |  | 0%
| Get roll out info for rest of the sites | Program Manager |  |  |  | 0% | 2025-09-12 | 2025-09-12
| Monitoring & Support |  |  |  | 0 | 0% | 2025-09-15 | 2025-10-15 | 31
Monitoring | Proactive Monitoring to make sure everything works fine - violations, alerts, notifications are getting generated correctily and all everything is showing up correctly in dashboard. | Support |  |  |  | 0% | 2025-09-15 | 2025-10-15 | 31
| Performance monitoring | Support |  |  |  | 0% | 2025-09-15 | 2025-10-15 | 31
Ticketing | Track the false alerts, issue Resolution | Support |  |  |  | 0% | 2025-09-15 | 2025-10-15 | 31
| Overall |  |  |  | 371 | 72% | 2025-04-17 | 2025-10-15 | 182
Insert new rows ABOVE this one
2018-01-13
Note on K6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Rollout Plan (hidden)
Frac Crews Rollout Plan
| 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01
Site 1 | bar: 2025-04-01 to 2025-06-01
Site 2 & 3 | bar: 2025-05-01 to 2025-07-01
Site 4 & 5 | bar: 2025-07-01 to 2025-08-01
Site 6-10 | bar: 2025-09-01 to 2025-10-01
Sites 11 - 25 | [14 empty] | Oct 25 - Jan 26 | 54 Sites | bar: 2025-10-01 to 2025-12-01
Sites 26 - 40 | [14 empty] | Aug 25 - Sep 25 | Stage Gate | bar: 2026-01-01 to 2026-03-01
Sites 41 - 60 | [14 empty] | 2025-07-25 | 3 Sites | bar: 2026-03-01 to 2026-05-01
| 2025-09-01: HWO KSA Rollout Plan | 4 Regions |  | # Sites
| 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | Rocky Mountain | James | 11
Site 1 | [14 empty] | North East | Jason | bar: 2025-04-01 to 2025-06-01
Sites 2-4 | [14 empty] | South Central | ??? | bar: 2025-06-01 to 2025-08-01
Sites 5-6 | bar: 2025-08-01 to 2025-09-01
Sites 7 - 10 | bar: 2025-10-01 to 2025-11-01
Sites 11 - 15 | bar: 2025-12-01 to 2026-02-01
Sites 16 - 24 | bar: 2026-02-01 to 2026-05-01
Coil Tubing Visual Inspection Pilot
[7 empty] | 2025-05-01 | 2025-06-01 | 2025-07-01
Pilot
Coil Tubing HSE
| 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01
Site 1 | bar: 2025-04-01 to 2025-06-01
Site 2 & 3 | bar: 2025-05-01 to 2025-07-01
Site 4 & 5 | bar: 2025-07-01 to 2025-08-01
Site 6-10 | bar: 2025-09-01 to 2025-10-01
Sites 11 - 25 | bar: 2025-10-01 to 2025-12-01

## MD (hidden)
Yet To Start
In Progress
Completed